## Chart of Tasks
Vote By Mail Project Timeline
| TASK | OUTSIDE Go/No Go | START | END | DURATION (weeks) | DEPENDENCY & PARTNERS | Month | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | Sept |  |  |  | October |  |  |  | November
[7 empty] | Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
[7 empty] | E- Date | -210 | -203 | -195 | -187 | -180 | -173 | -165 | -158 | -152 | -146 | -139 | -131 | -123 | -115 | -107 | -100 | -92 | -83 | -75 | -68 | -61 | -52 | -45 | -37 | -30 | -22 | -15 | -7 | GO | LIVE
Application for Ballot
Paper | bar: April 1 to April 2; June 1 to June 2
| Design usable form - to achieve high engagement level | X | -180 | -140 | 6 | CCD; Legal; Comms | bar: April 1 to April 2; May 1 to June 2
| Decide on distribution method; download; blank applications to housholds; preprinted direct mail in envelope; glossy postcard; etc; |  | -180 | -140 | 6 | Legal; Vendor | bar: April 1 to April 2; May 1 to June 2
| Contract for production & outbound mailing work; finalize specifications | X | -152 | -107 | 6 | Procurement; vendor | bar: April 1 to April 2; June 1 to July 2
| Outbound application envelope (if any) approval from USPS; consider non-profit, first class, business reply, etc. | X | -140 | -115 | 4 | USPS; CCD | bar: April 1 to April 2; June 1 to July 2
| Production of Materials |  | -107 | -55 | 7 | Vendor | bar: April 1 to April 2; June 1 to June 2; July 3 to Sept 2
| Applicantion Mail Drop |  | -55 | -40 | 2 | bar: April 1 to April 2; June 1 to June 2; Sept 2 to Sept 3
| Acceptance of Applications & Processing |  | -45 | -1 | 7 | bar: April 1 to April 2; June 1 to June 2; Sept 3 to November 1
| Considerations for a Remote Work Force; Planning and Production |  | -150 | -1 | 20 | County IT; Legal; State IT; State and Local Election Officials | bar: April 1 to April 2; June 1 to October 4
Online | bar: April 1 to April 2; June 1 to June 2
| Decide to add this to online service request |  | -210 | -195 | 3 | Policymaker | bar: April 1 to April 3; June 1 to June 2
| Change Laws/ Rules | X | -187 | -165 | 4 | Lawmakers; Executive; Policymakers | bar: April 1 to April 2; April 4 to May 3; June 1 to June 2
| Write Tech Specs & Iterate (with existing OVR) |  | -158 | -115 | 7 | ED; Vendor; IT; CISO | bar: April 1 to April 2; May 4 to July 2
| Write Code & Test (with existing OVR) |  | -123 | -83 | 8 | Vendor; IT; CISO | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4
| Write Tech Specs & Iterate (without OVR) |  | -187 | -115 | 11 | Vendor; IT; CISO | bar: April 1 to April 2; April 4 to July 2
| Write Code & Test (without OVR) |  | -152 | -83 | 12 | Vendor; IT; CISO | bar: April 1 to April 2; June 1 to August 4
| Go Live & Iterate |  | -75 | -7 | 10 | Vendor; IT | bar: April 1 to April 2; June 1 to June 2; August 1 to October 4
| Define & Train on process/procedures for converting digital data into VRDB |  | -75 | -45 | 4 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 2
| Considerations for a Remote Work Force; Planning and Production |  | -150 | -1 | 20 | County IT; Legal; State IT; State and Local Election Officials | bar: April 1 to April 2; June 1 to October 4
| Consider Partnering with CISA on Data Transfer (In transit and at rest); System and Network Security; Remote Penetration Testing; Vulnerability Scanning |  | -210 | -37 | 24 | CISO; CISA | bar: April 1 to Sept 4
| Consider Instituting Data Transit Best Practices |  | -150 | -37 | 16 | CISA | bar: April 1 to April 2; June 1 to Sept 4
| Establish Protocols for searching for improper application for ballots through data analytics; IP Addresses; Mail to Addresses; Signature Review; Confirmation Sampling |  | -37 | -7 | 4 | Election Officials; IT for Reports | bar: April 1 to April 2; June 1 to June 2; Sept 4 to October 3
Outbound Ballots - Logistics
Legislative, Policy, and Executive Actions | bar: April 1 to April 3; June 1 to June 2
| Decide New Policy & Estimate Impact |  | -210 | -195 | 3 | Policymaker | bar: April 1 to April 3; June 1 to June 2
| Change Laws/ Rules | X | -187 | -165 | 4 | Lawmakers; Executive; Policymakers | bar: April 1 to April 2; April 4 to May 3; June 1 to June 2
Envelopes & Inserts | bar: April 1 to April 2; June 1 to June 2
| Determine Highest Possible Count of Envelope & Materials | X | -180 | -150 | 5 | Election Officials | bar: April 1 to April 2; May 1 to June 2
| Contract for Prodcution of Envelopes & Materials |  | -210 | -140 | 6 | Vendor; Officials | bar: April 1 to June 3
| Artwork Approval with USPS; Business Approval - non profit, first class, business reply, etc. | X | -140 | -120 | 3 | Designers; USPS | bar: April 1 to April 2; June 1 to July 1
| Setup postage due account with USPS - undeliverables, return mail, etc. | X | -125 | -60 | 9 | USPS | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4
| Coordinate with USPS - PO Box, delivery dates, locations | X | -125 | -80 | 6 | USPS; Vendor | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4
| Design & Contract to produce stickers, inserts, etc. | X | -123 | -80 | 6 | Designers; vendors | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4
| Envelope Production |  | -80 | -66 | 3 | Print Vendor; Art Vendor; USPS | bar: April 1 to April 2; June 1 to June 2
| Other Materials Production; Inserts; Stickers |  | -80 | -66 | 3 | Print Vendor; Art Vendor; USPS | bar: April 1 to April 2; June 1 to June 2
| Delivery of Materials to Fulfillment Center |  | -75 | -61 | 2 | Vendor; Facility | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 1
Ballot Printing | bar: April 1 to April 2; June 1 to June 2
| Select and Certify Ballot Printer | X | -210 | -150 | 10 | Voting System Vendor | bar: April 1 to June 2
| Quantities for Paper Order | X | -100 | -90 | 2 | bar: April 1 to April 2; June 1 to June 2; July 4 to August 4
| Data for Print Quantity by Style |  |  | -75 | 1 | bar: April 1 to April 2; June 1 to June 2
| Ballot Images |  | -60 | -50 | 2 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 2
| Delivery to Fulfillment Center |  | -55 | -40 | 2 | bar: April 1 to April 2; June 1 to June 2
Fullfillment - Envelope Packaging & Mailing | bar: April 1 to April 2; June 1 to June 2
| Select and contract with fulfillment Center | X | -210 | -75 | 10 | bar: April 1 to August 4
| UOVAVA Data File sent to vendor |  | -55 | -55 | 1 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 2
| UOCAVA Ballots Packaged & Mailed |  | -55 | -45 | 2 | bar: April 1 to April 2; June 1 to June 2; Sept 3
| Initial mailing file sent to vendor |  | -55 | -35 | 3 | bar: April 1 to April 2; June 1 to June 2; Sept 2
| Daily update files sent to vendor |  | -35 | -5 | 5 | bar: April 1 to April 2; June 1 to June 2; Sept 2 to October 4
| Voter Ballots Packaged & Mailed - First Run |  | -55 | -29 | 4 | bar: April 1 to April 2; June 1 to June 2; Sept 2 to October 1
| Voter Ballots Packaged & Mailed - Supplemental |  | -28 | -5 | 3 | bar: April 1 to April 2; June 1 to June 2
| Last day to mail ballots |  | -5 | -5 | 1 | bar: April 1 to April 2; June 1 to June 2; October 4
Ballot tracking - If doing this will be part of Fullfullment | bar: April 1 to April 2; June 1 to June 2
| - contract with a vendor; USPS; Test | X | -107 | -55 |  | Vendor; USPS | bar: April 1 to April 2; June 1 to June 2; July 3 to Sept 2
| Upload file to ballot tracking software (repeated with every mail drop) |  | -45 | -1 |  | Vendor; USPS | bar: April 1 to April 2; June 1 to June 2; Sept 4 to October 4
Security Considerations | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 2
| Consider Partnering with CISA on Data Transfer (In transit and at rest); System and Network Security; Remote Penetration Testing; Vulnerability Scanning |  | -210 | -1 | 24 | CISO; CISA | bar: April 1 to Sept 4
| Consider Instituting Data Transit Best Practices |  | -152 | -1 | 16 | CISA | bar: April 1 to April 2; June 1 to Sept 4
| Establish Protocols for searching for improper application for ballots through data analytics; IP Addresses; Mail to Addresses; Signature Review; Confirmation Sampling |  | -30 | -1 | 4 | Election Officials; IT for Reports | bar: April 1 to April 2; June 1 to June 2; Sept 4 to October 3
Inbound Ballot Process
| Establish date Ballot Processing can begin |  | -210 | -165 | 6 | Policymaker | bar: April 1 to May 2
| Analyze space and staffing needs based upon expected volume of returned ballots | X | -165 | -139 | 4 | Facilities Management; | bar: May 3 to June 4
| Procure high-speed scanner(s) - timeframe depends on the vendor; COTS systems available more readily than proprietary builds | X | -107 | -45 | 12 | Procurement; Vendor Product Availability; Other Agencies if Shared | bar: July 3 to Sept 2
| Procure and install envelope sorting equipment (in jurisdictions expecting 75,000 or more returned ballots) | X | -139 | -45 | 12 | Procurement; Vendor Product Availability; Other Agencies if Shared | bar: June 1 to Sept 2
| Procure and install an envelope slicer (in jurisdicitons not using envelope sorting equipment) |  | -100 | -37 | 8 | Procurement; Vendor Product Availability; Other Agencies if Shared | bar: July 4 to Sept 3
| Document procedures for Ballot Processing - training, setup, ballot tracking/accounting, secure transfer of ballots, organization and storage |  | -100 | -37 | 8 | bar: July 4 to Sept 3
| Purchase or rent supplies - mail trays, storage carts, folding tables and chairs, and ballot storage, etc. |  | -92 | -30 | 8 | Procurement; Product Availability | bar: August 1 to October 4
| Hire and train Inbound Ballot Processing teams |  | -83 | -22 | 8 | bar: August 1 to October 4
| Perform logic and accuracy test on scanning equipment |  | -52 | -45 | 1 | bar: Sept 3
| Perform full test of system prior to ballot processing to ensure you can capture voter information (barcode) and signatures from the envelope and definitions for sorting ballots are working (if using ballot sorting equipment) |  | -37 | -30 | 1 | Vendor; VRDB | bar: Sept 4 to October 4
| Perform a full dry run of the Inbound Ballot Process - ballot receiving, ballot verification, ballot preparation, ballot scanning, ballot tabulation, and post-election audit, etc. |  | -30 | -22 | 2
| Perform daily inbound ballot process; able to scale up on Election Day |  | -22 | 4 | 7 | bar: October 1 to November 4
Signature Verification & Cure Process
| Purchase automated signature verification software if using mail ballot sorting equipment |  | -152 | -37 | 15 | Procurement; Vendor Product Availability; Other Agencies if Shared | bar: April 1 to April 2; June 1 to Sept 3
| Review VRDB for voters with no archived signature image. Consider sending an affidavit or new VR form to those missing a signature image. |  | -123 | -92 | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4
| Document Signature Verification and Cure process - training, audits, secure transfer of ballots, and templates for cure letters, etc. |  | -92 | -30 | 8 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 4
| Create daily system for cure letters going out and signed affidavits coming in to ensure cured ballots are regularly transferred for processing |  | -61 | -30 | 4 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 4
| Hire and train Signature Verification teams |  | -68 | -15 | 8 | bar: April 1 to April 2; June 1 to June 2; August 1 to October 3
| Perform full test of system prior to ballot processing to ensure you can capture the signature image from the envelope (if using signature verification software) |  | -37 | -30 | 1 | bar: April 1 to April 2; June 1 to June 2; Sept 4
| Perform test to insure the correct voter file and archived signature image can be retrieved for signature comparison (required for both automated and manual process) |  | -37 | -30 | 1 | Vendor; VRDB | bar: April 1 to April 2; June 1 to June 2; Sept 4 to October 2
| Test any software used to notify voters of signature discrepancy or assit with the cure process - ballot tracking tools, text-to-cure app, etc. |  | -30 | -22 | 2 | Vendor | bar: April 1 to April 2; June 1 to June 2; October 1 to October 2
| Perform daily signature verification and send/receive cure letters and affidavits |  | -15 | 4+ | 6+ | bar: April 1 to April 2; June 1 to June 2; October 3 to November 4
Online Ballot Delivery
| Determine eligibility rules |  | -210 | -180 | 4 | Lawmakers; Executive; Policymakers | bar: April 1 to April 2; June 1 to June 2
| Determine transmission types - email, fax, online portal, telephonic, etc. |  | -210 | -180 | 4 | Lawmakers; Executive; Policymakers | bar: June 1 to June 2
| Change laws/rules | X | -210 | -180 | 4 | Lawmakers; Executive; Policymakers | bar: June 1 to June 2
| System selection - choose vendor or build in-house | X | -210 | -180 | 4 | bar: June 1 to June 2
| Update voter files to reflect e-ballot delivery status |  | -210 | -1 | 28 | bar: April 1 to October 4
| Provide voter credentials to access e-ballots |  | -29 | 0 | 6 | bar: April 1 to April 2; June 1 to June 2; October 1 to November 2
| Consider Partnering with CISA on Data Transfer (In transit and at rest); System and Network Security; Remote Penetration Testing; Vulnerability Scanning |  | -210 | -37 | 24 | CISO; CISA | bar: April 1 to Sept 4
| Consider Instituting Data Transit Best Practices |  | -150 | -37 | 16 | CISA | bar: April 1 to April 2; June 1 to Sept 4
| Build ballot definition files |  | -120 | -46 | 11 | Vendor; IT | bar: April 1 to April 2; June 1 to June 2; July 1 to Sept 3
| L&A ballot files/electronic interface |  | -60 | -35 | 4 | Vendor; IT; Ballot printer | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 4
| Distribute electronic ballots |  | -29 | 0 | 6 | Vendor; IT | bar: April 1 to April 2; June 1 to June 2; October 1 to November 2
Voter Education
Conduct a voter education and outreach campaign | bar: April 1 to April 2; June 1 to June 2
Ballot Drop Box
| Determine the number of ballot drop boxes you need or are required to have |  | -210 | -180 | 4 | Admin Rule; # registered voters
| Determine the type(s) of ballot drop boxes and where they will be located |  | -210 | -180 | 4 | Available locations; budget
| 24 Hour Boxes | X | bar: April 1 to April 2; October 1 to October 3
| Obtain necessary permits or approvals |  | -180 | -152 | 4 | bar: April 1 to April 2; May 1 to June 4; October 1 to October 3
| Purchase supplies - dropbox, camera & data storage device, etc. |  | -180 | -92 | 12 | Permit obtained | bar: April 1 to April 2; May 1 to August 4; October 1 to October 3
| Install permanent dropbox; cameras; apply decals |  | -92 | -30 | 8 | bar: April 1 to April 2; June 1 to June 2; August 1 to October 3
| Outdoor Drive-Through Drop Off | X | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3
| Coordinate a traffic plan with public safety officials |  | -123 | -92 | 4 | bar: April 1 to April 2; June 1 to June 2; July 1 to August 4; October 1 to October 3
| Purchase ballot box |  | -107 | -45 | 8 | Public safety | bar: April 1 to April 2; June 1 to June 2; July 3 to Sept 2; October 1 to October 3
| Arrange to borrow traffic signs and cones |  | -61 | -30 | 4 | bar: April 1 to April 2; June 1 to June 2; August 1 to October 3
| Purchase or rent supplies - tent, tables, chairs, heater, etc. |  | -61 | -30 | 4 | bar: April 1 to April 2; June 1 to June 2; August 1 to October 3
| Hire/recruit staff to man the tent |  | -45 | -22 | 3 | bar: April 1 to April 2; June 1 to June 2; Sept 3 to October 3
| Temporary, Indoor Boxes | X | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3
| Make arrangements with facility (should include care facility) |  | -158 | -107 | 7 | bar: April 1 to April 2; May 4 to July 2; October 1 to October 3
| Purchase ballot box |  | -107 | -45 | 8 | Facility | bar: April 1 to April 2; June 1 to June 2; July 3 to Sept 2; October 1 to October 3
| Purchase locks and chains if needed |  | -61 | -45 | 2 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 2; October 1 to October 3
Ballot Box Collection Teams | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3
| Create a ballot collection plan to include daily routes and frequency of collection |  | -92 | -37 | 7 | # of boxes/collection frequency | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 3; October 1 to October 3
| Based on collection plan, hire enough drivers to create two person teams |  | -61 | -30 | 4 | # of collection teams | bar: April 1 to April 2; June 1 to June 2; August 1 to October 3
| Arrange for enough vehicles from county fleet or rental car agency |  | -61 | -37 | 3 | bar: April 1 to April 2; June 1 to June 2; August 1 to Sept 3; October 1 to October 3
| Make arrangements to rent or borrow radios or cell phones (or arrange for cell phone stipend) |  | -37 | -22 | 3 | bar: April 1 to April 2; June 1 to June 2; Sept 4 to October 3
| Prepare ballot pickup team supplies and logs |  | -30 | -22 | 2 | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3
| Start daily USPS ballot pickup (including undeliverable ballots) |  | -22 | 4+ | 7+ | USPS | bar: April 1 to April 2; June 1 to June 2; October 1 to November 4
| Send drivers to open 24 hr boxes; setup drive through tents; or deliver temporary boxes |  | -29 | -27 | 1 | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3
| Final ballot drop box pickup and closure |  | 0 | 0 | 0 | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3; November 3
| Final USPS pickup |  | 1 | bar: April 1 to April 2; June 1 to June 2; October 1 to October 3; November 4
Voter List Maintenance
| Process NCOA list |  |  | -60 | bar: April 1 to April 2; June 1 to June 2
CASS Certificaiton | bar: April 1 to April 2; June 1 to June 2